## Sheet1
Gantt Chart
AEM4331 CubeSat Senior Design
University of Minnesota
TASK | DESCRIPTION | TASKEE | Start Date | End Date | Duration(days) | % Complete | Working Days | Days Passed | Days Remain
1 | SubGroup Divisions | All | 2015-09-05 | 2015-09-11 | 7 | 100% | 5 | 7 | 0
1.1 | Associate with system subgroup |  | 2015-09-05 | 2015-09-11 | 7 | 100% | 5 | 7 | 0
1.1.1 | Research CubeSat substructures |  | 2015-09-05 | 2015-09-09 | 5 | 100% | 3 | 5 | 0
2 | Research and Implement Information |  | 2015-09-10 | 2015-12-10 | 92 | 31.72% | 66 | 29 | 63
2.1 | Structure | STRUCT | 2015-09-10 | 2015-11-08 | 60 | 60% | 42 | 36 | 24
2.1.1 | Designate pwr and com requirements | STRUCT | 2015-10-01 | 2015-10-20 | 20 | 25% | 14 | 5 | 15
2.1.1.1 | Design a suitable Structure for NASA req. | STRUCT | 2015-10-09 | 2015-12-07 | 60 | 10% | 42 | 6 | 54
2.1.1.2 | Gather NASA NCLI req. for launch | STRUCT | 2015-09-15 | 2015-09-22 | 8 | 100% | 6 | 8 | 0
2.1.1.3 | Space budget of entire payload volume | STRUCT | 2015-09-15 | 2015-09-22 | 8 | 100% | 6 | 8 | 0
2.2 | ADNCS | ADNCS | 2015-09-10 | 2015-11-08 | 60 | 60% | 42 | 36 | 24
2.2.1 | Designate pwr and com requirements | ADNCS | 2015-10-01 | 2015-10-20 | 20 | 25% | 14 | 5 | 15
2.2.1.1 | Develop AD algorithms | ADNCS | 2015-10-09 | 2015-12-07 | 60 | 10% | 42 | 6 | 54
2.2.1.2 | Develop Skeleton Code for ADNCS hardware | ADNCS | 2015-11-01 | 2015-12-10 | 40 | 0% | 29 | 0 | 40
2.3 | Communication | COM | 2015-09-10 | 2015-11-08 | 60 | 75% | 42 | 45 | 15
2.3.1 | HardWare |  | 2015-10-01 | 2015-10-07 | 7 | 0% | 5 | 0 | 7
2.3.1.1 | Designate pwr and com requirements | COM | 2015-10-01 | 2015-10-20 | 20 | 25% | 14 | 5 | 15
2.3.1.2 | Develop COM algorithms | COM | 2015-10-09 | 2015-12-07 | 60 | 10% | 42 | 6 | 54
2.3.1.3 | Develop Skeleton Code for COM hardware | COM | 2015-11-01 | 2015-12-10 | 40 | 50% | 29 | 20 | 20
2.3.2 | Link Budget | COM | 2015-09-15 | 2015-11-13 | 60 | 0% | 44 | 0 | 60
2.4 | Power Management | PWR | 2015-09-10 | 2015-11-08 | 60 | 75% | 42 | 45 | 15
2.4.1 | Designate pwr and com requirements | PWR | 2015-10-01 | 2015-10-20 | 20 | 25% | 14 | 5 | 15
2.4.1.1 | Develop PWR algorithms | PWR | 2015-10-09 | 2015-12-07 | 60 | 10% | 42 | 6 | 54
2.4.1.2 | Develop Skeleton Code for ADNCS hardware | PWR | 2015-11-01 | 2015-12-10 | 40 | 0% | 29 | 0 | 40
3 | Lab Testing |  | 2015-11-01 | 2015-12-19 | 49 | 0% | 35 | 0 | 49
3.1 | ADNCS | ADNCS | 2015-11-01 | 2015-12-10 | 40 | 0% | 29 | 0 | 40
3.1.1 | Simulation of Attitude Determination | ADNCS | 2015-11-10 | 2015-12-19 | 40 | 0% | 29 | 0 | 40
3.2 | COM | COM | 2015-11-01 | 2015-12-10 | 40 | 0% | 29 | 0 | 40
3.2.1 | BreadBoard Test of Radio Communication | COM | 2015-11-10 | 2015-12-19 | 40 | 0% | 29 | 0 | 40
3.3 | PWR | PWR | 2015-11-01 | 2015-12-10 | 40 | 0% | 29 | 0 | 40
3.3.1 | Simulation of PWR Algorithms | PWR | 2015-11-10 | 2015-12-19 | 40 | 0% | 29 | 0 | 40
3.4 | Structure | PWR | 2015-11-01 | 2015-12-10 | 40 | 0% | 29 | 0 | 40
3.4.1 | Three Dimensional model of all components | PWR | 2015-11-10 | 2015-12-19 | 40 | 0% | 29 | 0 | 40
4 | PDR Presentation | ALL | 2015-10-01 | 2015-10-16 | 16 | 100% | 12 | 16 | 0
4.1 | IN CLASS PRESENTAION |  | 2015-10-16 | 2015-10-16 | 1 | 100% | 1 | 1 | 0
4.1.1 | Make revisions suggested from 4.2 |  | 2015-10-09 | 2015-10-16 | 8 | 100% | 6 | 8 | 0
4.1.1.1 | Intro/Outline | Charlie | 2015-10-09 | 2015-10-16 | 8 | 100% | 6 | 8 | 0
4.1.1.2 | ADNCS slides | ADNCS | 2015-10-09 | 2015-10-16 | 8 | 100% | 6 | 8 | 0
4.1.1.3 | COM Slides | COM | 2015-10-09 | 2015-10-16 | 8 | 100% | 6 | 8 | 0
4.1.1.4 | PWR Slides | PWR | 2015-10-09 | 2015-10-16 | 8 | 100% | 6 | 8 | 0
4.2 | Pre-Presentation |  | 2015-10-09 | 2015-10-09 | 1 | 100% | 1 | 1 | 0
4.2.1 | Assemble PowerPoint Presentation | All | 2015-10-08 | 2015-10-08 | 1 | 100% | 1 | 1 | 0
4.2.1.1 | Intro/Outline | Charlie | 2015-10-01 | 2015-10-03 | 3 | 100% | 2 | 3 | 0
4.2.1.2 | ADNCS slides | ADNCS | 2015-10-03 | 2015-10-07 | 5 | 100% | 3 | 5 | 0
4.2.1.3 | COM Slides | COM | 2015-10-03 | 2015-10-07 | 5 | 100% | 3 | 5 | 0
4.2.1.4 | PWR Slides | PWR | 2015-10-03 | 2015-10-07 | 5 | 100% | 3 | 5 | 0
5 | CDR Presentation | ALL | 2015-12-01 | 2015-12-15 | 15 | 0% | 11 | 0 | 15
5.1 | IN CLASS PRESENTAION |  | 2015-12-15 | 2015-12-15 | 1 | 0% | 1 | 0 | 1
5.1.1 | Prepare CDR | ALL | 2015-12-01 | 2015-12-15 | 15 | 0% | 11 | 0 | 15
6 | End of Semester ONE |  | 2015-12-15 | 2015-12-15 | 1 | 0% | 1 | 0 | 1
7 | Purchase Core Products |  | 2016-01-01 | 2016-02-01 | 32 | 0% | 22 | 0 | 32
7.1 | Source and order CORE products |  | 2016-01-01 | 2016-02-01 | 32 | 0% | 22 | 0 | 32
7.1.1 | Flight Computer |  | 2016-01-01 | 2016-02-01 | 32 | 0% | 22 | 0 | 32
7.1.2 | Power Management Board |  | 2016-01-01 | 2016-02-01 | 32 | 0% | 22 | 0 | 32
8 | Purchase NON-Core Products |  | 2016-02-01 | 2016-03-03 | 32 | 0% | 24 | 0 | 32
8.1 | Source and order NON-CORE products |  | 2016-02-01 | 2016-03-03 | 32 | 0% | 24 | 0 | 32
8.1.1 | Solar Panels with Solar Sensors |  | 2016-02-01 | 2016-03-03 | 32 | 0% | 24 | 0 | 32
8.1.2 | Timing Board (PCB) |  | 2016-02-01 | 2016-03-03 | 32 | 0% | 24 | 0 | 32
9 | Purchase Remaining Products |  | 2016-03-01 | 2016-05-10 | 71 | 0% | 51 | 0 | 71
9.1 | Source and order remaining products |  | 2016-03-01 | 2016-04-01 | 32 | 0% | 24 | 0 | 32
9.1.1 | CubeSat Structure |  | 2016-03-01 | 2016-04-01 | 32 | 0% | 24 | 0 | 32
9.1.2 | PWR Batteries |  | 2016-03-01 | 2016-04-01 | 32 | 0% | 24 | 0 | 32
10 | Assemble and CODE CubeSat |  | 2016-02-01 | 2016-05-10 | 100 | 0% | 72 | 0 | 100
10.1 | This is the Majority of Spring Semester (implementation) |  | 2016-02-01 | 2016-05-10 | 100 | 0% | 72 | 0 | 100
TEMPLATE ROWS: Copy and insert the entire section, or just the specific sub tasks, depending on which level you want to use (formulas are different for different WBS levels)
1 | Task Category 1 |  | 2015-01-01 | 2015-01-07 | 7 | 0% | 5 | 0 | 7
1.1 | Sub Task level 2 |  | 2015-01-01 | 2015-01-07 | 7 | 0% | 5 | 0 | 7
1.1.1 | Level 3 Task |  | 2015-01-01 | 2015-01-07 | 7 | 0% | 5 | 0 | 7
1.1.1.1 | Level 4 task |  | 2015-01-01 | 2015-01-07 | 7 | 0% | 5 | 0 | 7
Formulas:
Start Date = MIN([Start Date, row below]:D7)
End Date = [Start Date]+[Duration(days)]-1
Working Days = NETWORKDAYS([Start Date],[End Date])